# RESUME2WEBSITE Kubernetes Migration - Bullet Points Summary

## Pre-Handover Checklist

### Code Cleanup

• Remove all hardcoded secrets (Stripe keys, API keys, passwords)

• Create .env.example template with all required environment variables

• Search for sensitive data: `grep -r "sk_" .` and `grep -r "secret" .`

### Documentation Required

• System requirements document (Python 3.11+, Node.js 18+, PostgreSQL 14+)

• Critical business logic documentation

• Performance requirements (CV extraction: 40-60s, Portfolio: 2-3 min)

• Known issues and limitations document

### Code Preparation

• Create database abstraction layer (DatabaseInterface class)

• Create storage abstraction layer (StorageInterface class)

• Add integration test suite for critical paths

• Document all dependencies (requirements.txt, package.json)

## DevOps Responsibilities

### Infrastructure Setup

• Create VPC with public/private subnets

• Set up EKS/ECS cluster

• Configure RDS Aurora PostgreSQL

• Set up ElastiCache Redis cluster

• Create S3 buckets for file storage

• Configure CloudFront CDN

• Set up ALB/NLB load balancers

• Configure Route53 DNS records

• Generate ACM SSL certificates

• Create IAM roles and policies

### Containerization

• Create optimized Dockerfiles with multi-stage builds

• Implement security scanning (Trivy/Snyk)

• Configure non-root users

• Add health checks

• Optimize layer caching

### Database Migration

• Convert SQLite schema to PostgreSQL

• Create data migration scripts

• Set up connection pooling

• Configure read replicas if needed

• Implement backup strategies

### Kubernetes/ECS Configuration

• Create deployment manifests

• Define service configurations

• Set up Ingress/ALB

• Configure HPA (Horizontal Pod Autoscaler)

• Create ConfigMaps and Secrets

• Implement NetworkPolicies

• Set up Helm charts or Kustomize

### CI/CD Pipeline

• Set up GitHub Actions/GitLab CI

• Implement automated testing

• Configure Docker image building

• Add security scanning

• Create staging deployments

• Add approval gates

• Set up production deployments

• Create rollback procedures

## Critical Challenges

### Portfolio Generation System

• **Current Problem**: Spawns Next.js instances on ports 4000-5000

• **Issue**: Dynamic port allocation doesn't work in Kubernetes

• **Solution Options**:

- Static generation with S3 hosting

- Kubernetes Jobs for portfolio building

- Lambda functions for generation

### Stateful Components

• **SQLite Database**: Must migrate to RDS/Aurora

• **Local File Storage**: Must move to S3

• **Session Management**: Must use Redis/ElastiCache

• **Sandbox Directories**: Need S3 or EFS for temporary storage

## Migration Phases

### Phase 1: Preparation (Weeks 1-2)

• Set up AWS account and IAM roles

• Create RDS Aurora instance

• Configure S3 buckets

• Set up ElastiCache

• Update code with environment variables

### Phase 2: Containerization (Weeks 3-4)

• Create Dockerfiles for backend/frontend

• Build and test containers locally

• Push to ECR repository

• Test with docker-compose

### Phase 3: Infrastructure (Weeks 5-6)

• Create EKS/ECS cluster

• Deploy core services

• Configure networking

• Set up monitoring

### Phase 4: Deployment (Weeks 7-8)

• Deploy to staging

• Run integration tests

• Perform load testing

• Fix identified issues

### Phase 5: Migration (Weeks 9-10)

• Migrate data from SQLite to RDS

• Migrate files to S3

• DNS cutover

• Monitor for 48 hours

### Phase 6: Optimization (Weeks 11-12)

• Tune auto-scaling

• Optimize costs

• Implement caching

• Complete documentation

## Cost Estimates

### AWS Services Monthly Costs

• EKS Cluster: $144

• EC2 Nodes (3x t3.medium Spot): $90

• RDS Aurora Serverless v2: $150

• S3 Storage (100GB): $25

• ElastiCache (t3.micro): $25

• CloudFront (100GB transfer): $10

• ALB Load Balancer: $25

• NAT Gateway: $45

• **Total**: ~$514/month

### Cost Optimization Strategies

• Use Spot Instances (70% savings)

• Aurora Serverless v2 (scales to zero)

• S3 Intelligent-Tiering for old files

• Reserved Instances for predictable workloads

• Consider Lambda for portfolio generation

## Critical Files for DevOps Review

### Backend

• `config.py` - All configuration

• `main.py` - FastAPI entry point

• `src/api/routes/portfolio_generator.py` - Portfolio generation (BIGGEST CHALLENGE)

• `src/api/routes/cv.py` - File upload handling

• `src/api/db.py` - Database operations

• `src/core/cv_extraction/data_extractor.py` - Claude API integration

### Frontend

• `user_web_example/package.json` - Dependencies

• `user_web_example/app/page.tsx` - Main app entry

• `user_web_example/.env.local` - Frontend environment

## Critical Warnings

• **DON'T** change CV data structure (18 sections hardcoded)

• **DON'T** change Claude model (must be Claude 4 Opus, temperature 0.0)

• **DON'T** break portfolio preview flow

• **CAREFUL** with package managers (main: pnpm, sandboxes: npm)

• **PRESERVE** uploaded CVs (users expect persistence)

• **TEST** payment webhooks thoroughly (Stripe critical)

## Success Criteria

### Phase 1: Basic Functionality

• Application runs in Kubernetes/ECS

• Database migrated to RDS

• Files stored in S3

• Sessions in Redis

• Health checks passing

### Phase 2: Full Functionality

• CV upload and extraction working

• Portfolio generation working

• Payment processing working

• OAuth login working

• All API endpoints responding

### Phase 3: Production Ready

• Auto-scaling configured

• Monitoring dashboards live

• Alerts configured

• Backup strategy in place

• Disaster recovery tested

• Documentation complete

## Communication Protocol

### Initial Meeting Topics

• Architecture overview and data flow

• Critical business requirements

• Current pain points (especially portfolio sandboxes)

• Performance requirements

• Security requirements

• Questions for DevOps team

### Access Requirements

• GitHub repository (read/write)

• AWS account credentials

• Vercel account (if keeping)

• Stripe webhook endpoints

• OAuth app credentials

• Domain registrar access

## Key Decisions Needed

### Infrastructure Choices

• **EKS vs ECS**: ECS recommended (simpler, cheaper)

• **Database**: Aurora Serverless v2 recommended

• **File Storage**: S3 with CloudFront CDN

• **Sessions**: ElastiCache Redis

• **Portfolio Generation**: Needs complete redesign

### Technical Decisions

• Replace Vercel deployment with native K8s/S3

• Use static builds instead of dynamic ports

• Implement circuit breakers for all external APIs

• Add distributed tracing for debugging

## Timeline & Resources

• **Total Duration**: 8-12 weeks

• **Team Required**: 2-3 developers + 1 DevOps lead

• **Monthly AWS Cost**: $500-$1,500

• **Risk Level**: Medium-High (due to portfolio sandbox complexity)

## Final Recommendations

• Start with ECS Fargate instead of EKS (simpler management)

• Portfolio generation works better with ECS Tasks than K8s Jobs

• Consider Lambda for portfolio generation if possible

• Implement gradual migration (database first, then files, then compute)

• Keep Vercel for final deployment, use S3 for previews

• Set up comprehensive monitoring before migration